## Summary
HR Migration Gap Analysis — Summary
LEGACY .NET
Total Controllers | 103
Total Action Methods | 995
GET Methods | 565 (56.8%)
POST Methods | 430 (43.2%)
Authorized Methods | 665 (66.8%)
View Files (.cshtml) | 282
Business Object Classes | 145
MODERN GO + NEXT.JS
Go API Endpoints | 95
Repository Methods (SQL) | 189 (in 143KB file)
Next.js Pages | 47+
Shared UI Components | 6 (288KB total)
Server Actions | 100+
GAP ANALYSIS
Controllers Fully Migrated | ~35 (34%)
Controllers Partially Migrated | ~32 (31%)
Controllers Missing | ~36 (35%)
Missing Action Methods | ~350+
Missing Features (#) | 35
Total Effort to Close Gaps | ~175 developer-days
Estimated Duration | 16 weeks (8 sprints)
TOP 3 CRITICAL BLOCKERS
1. No background job framework | Mobile attendance won't post to daily records
2. No auto-close attendance | Open sessions corrupt salary calculations
3. No biometric import | Manual attendance entry only — defeats automation

## Controller Mapping
# | Legacy Controller | Methods | Legacy File | Modern Go Endpoint(s) | Modern Next.js Page | Status | What's Missing | Migration Plan
EMPLOYEE MANAGEMENT — 18 Legacy Controllers, 170 Methods
1 | EmployeeController | 28 | EmployeeController.cs | employees-list, employee-save, employee-delete, employee-get | /hr/employees, /hr/employees/new, /hr/employees/[id]/edit | Partial | ExcelDownload, EmployeeCardView, EmployeeProfile, SendSMStoEditProfile, EditEmployee (alternate), ShowEmployeeDetailOnPopUp, SDFDList/SDFEList/SDVDList/SDVEList/SDLAList (sub-detail views), ShowNetAmount, WorkFlowRemarks | 1. Add Excel download endpoint 2. Build card view layout 3. Implement employee profile page 4. Add sub-detail list views (fixed/variable earning/deduction/loan) 5. Implement workflow remarks
2 | EmployeeEducationController | 8 | EmployeeEducationController.cs | employee-save (education tab) | /hr/employees/[id]/edit (tab) | Partial | Separate Document upload/view (DocList, Document, ShowEmployeeDocumentOnPopup, DeleteDocument) — verify all work in modern form tab. Legacy has 8 dedicated methods. | Verify education tab CRUD + document upload in employee form works for add/edit/delete/view
3 | EmployeefamilyController | 8 | EmployeefamilyController.cs | employee-save (family tab) | /hr/employees/[id]/edit (tab) | Partial | DocList, Document, ShowEmployeeDocumentOnPopup, RelationList — family document management. Legacy has separate relation list endpoint. | Verify family tab includes document uploads, relation type dropdown, and all CRUD operations
4 | EmployeePreviousExperienceController | 4 | EmployeePreviousExperienceController.cs | employee-save (prev emp tab) | /hr/employees/[id]/edit (tab) | Migrated | Legacy has GetData/List/Edit/Index — modern uses inline form fields (2 previous employers hardcoded in form) | Verify previous experience tab saves correctly — modern uses fixed 2-employer layout vs legacy dynamic list
5 | EmployeeSalaryController | 4 | EmployeeSalaryController.cs | salary-fixation-details | /hr/salary-fixation (detail) | Migrated | GetData, List, Edit, Index — basic salary viewing | Covered by salary fixation detail view
6 | EmployeeSalaryTrackingController | 23 | EmployeeSalaryTrackingController.cs | salary-tracking-list, salary-fixation-save, salary-slip-pdf, salary-slip-data | /hr/salary-tracking, /hr/salary-fixation | Partial | GetEmployeeSalaryTrackingHistory, GetSalarySlipHtml, ExcelDownload, SDFDList/SDFEList/SDVDList/SDVEList/SDLAList (sub-detail), ShowNetAmount — 23 methods vs ~6 modern endpoints | 1. Add salary history endpoint 2. Verify salary slip PDF generation 3. Add Excel export 4. Build sub-detail earning/deduction views
7 | EmployeeSalaryTrackingDetailController | 4 | EmployeeSalaryTrackingDetailController.cs | salary-fixation-details | /hr/salary-fixation (detail table) | Migrated | GetData, List, Edit — covered by fixation detail | Verify detail view shows all columns
8 | EmployeeTypeController | 14 | EmployeeTypeController.cs | employee-type-save/list/delete, masters | /hr/employee-types | Partial | RecalculateSalary, RecalculateSalaryProcess, LongRunningProcess — salary recalculation by employee type not in modern | Implement salary recalculation when employee type changes (cascading salary update)
9 | EmployeeTypeDetailController | 11 | EmployeeTypeDetailController.cs | salary-fixation-details (implied) | — | Missing | FDIndex/FDList, FEIndex/FEList, VDIndex/VDList, VEIndex/VEList, ShowFormulaEditor — Employee Type salary structure (FD=Fixed Deduction, FE=Fixed Earning, VD/VE) | Build employee type detail views showing earning/deduction breakdowns with formula editor
10 | EmployeeTypeATController | 4 | EmployeeTypeATController.cs | — | — | Missing | Attendance Type per Employee Type configuration (GetData, Index, List, Edit) | Build attendance-type-per-employee-type mapping CRUD
11 | EmployeeAttendanceController | 11 | EmployeeAttendanceController.cs | daily-attendance-list (with employee filter) | /hr/daily-attendance (filtered) | Partial | ExcelDownload, dedicated per-employee attendance CRUD separate from daily attendance | Verify daily attendance page supports employee-specific filtering and editing
12 | EmployeeAttendanceDetailController | 5 | EmployeeAttendanceDetailController.cs | — | — | Missing | GetData, GetEmployeeCode, Index, List, Edit — detailed per-employee attendance editing | Build employee attendance detail view or verify it's covered by daily attendance edit
13 | EmployeeAttendanceListController | 5 | EmployeeAttendanceListController.cs | — | — | Missing | Init, Index, AutoComplete, Download, Navigate — employee-wise attendance list report | Build employee attendance list report with filters and Excel download
14 | EmployeeIncentiveOTController | 14 | EmployeeIncentiveOTController.cs | overtime-save/list/delete | /hr/overtime | Partial | ExcelDownload, IndexCardView, MenuTreeList, GetPerHourSalaryJson — incentive calculation, card view | 1. Add per-hour salary calculation endpoint 2. Add Excel download 3. Verify incentive+OT combined logic
15 | EmployeeImportedAttendanceListController | 5 | EmployeeImportedAttendanceListController.cs | import-attendance-batches-list | /hr/import-attendance | Partial | Separate Init/AutoComplete/Download/Navigate endpoints for imported records list | Verify import attendance page shows historical imported records
16 | EmployeeSummaryListController | 5 | EmployeeSummaryListController.cs | — | — | Missing | Init, Index, AutoComplete, Download, Navigate — employee summary report | Build employee summary report page
17 | EmployeeAssetController | 4 | EmployeeAssetController.cs | employee-asset-save/list/delete | /hr/employee-asset | Migrated | GetData, Index, List, Edit — basic CRUD present | Verify all fields match
18 | EmployeeFineController | 13 | EmployeeFineController.cs | employee-fine-save/list/delete, employee-fine-waive, employee-fines-v2-* | /hr/employee-fines | Migrated | ExcelDownload, IndexCardView, MenuTreeList — card view layout and Excel export missing | Add Excel download and card view layout
ATTENDANCE & TIME — 18 Legacy Controllers, 174 Methods
19 | AttendanceController | 55 | AttendanceController.cs | daily-attendance-save/list/delete, import-attendance-*, mobile-attendance-list | /hr/daily-attendance, /hr/import-attendance | Partial | 55 methods — MAJOR GAPS: AutoCloseAttendance, DailyAttendanceReport, MonthlyAttendance, MonthlyAttendanceReport(+Download), ODAttendancePopup, DailyAttendanceV2, _DailyAttendanceV2/_DailyAttendanceV2Edit, LEAP, ImportDailyAttendance, ImportFromMobileAttendance(+Old+MissedSalary), SaveMissedDaysAttendance, UpdateAttendanceVerified, DeleteAttendanceCompleted, CalculatePermissionUtilized, CheckIfPendingApprovalsExists, CheckSalaryFixationIsMissing, AttendanceCompletedEntryPopup, ShowEmployeeDetailOnPopUp, MarkAsAbsent, GetDailyAttendance, EmployeeDailyAttendance, SaveEmployeeDailyAttendanceReportEdit | CRITICAL: 1. Build AutoCloseAttendance 2. Build Monthly Attendance view + report 3. Build DailyAttendanceReport (printable) 4. Port DailyAttendanceV2 (new version) 5. Build mark-as-absent endpoint 6. Build attendance verification system 7. Build OD popup 8. Build LEAP view
20 | DailyAttendanceController | 11 | DailyAttendanceController.cs | daily-attendance-save/list/delete | /hr/daily-attendance | Migrated | ExcelDownload missing. Standard CRUD present. | Add Excel download
21 | DailyAttendanceDetailController | 6 | DailyAttendanceDetailController.cs | — | — | Missing | GetData, GetEmployeeCode, Index, List, Summary, Edit — detailed attendance per employee with summary | Build daily attendance detail view with employee summary
22 | AttendanceListController | 4 | AttendanceListController.cs | — | — | Missing | Init, Index, Download, Navigate — attendance list report | Build attendance list report page
23 | AttendanceListForaPeriodController | 5 | AttendanceListForaPeriodController.cs | — | — | Missing | Init, Index, AutoComplete, Download, Navigate — period-based attendance report | Build period attendance report with date range filters and Excel download
24 | AttendanceSummaryListController | 2 | AttendanceSummaryListController.cs | — | — | Missing | Index, DownloadTemplate — attendance summary report with template download | Build attendance summary report page
25 | AttendanceTypeController | 11 | AttendanceTypeController.cs | attendance-type-save/list/delete, masters | /hr/attendance-types | Migrated | ExcelDownload missing | Add Excel download
26 | AttendanceFineWaiverController | 5 | AttendanceFineWaiverController.cs | employee-fine-waive | /hr/employee-fines (waive action) | Partial | Separate Index/Details/Edit views for fine waiver — legacy has dedicated page, modern uses inline action | Verify waive action works correctly with approval flow
27 | AttendanceNotPostedPeriodListController | 6 | AttendanceNotPostedPeriodListController.cs | — | — | Missing | Init, Index, AutoComplete, Download, Navigate, PostAttendance — list unposted attendance for period + ability to post | Build unposted attendance report with post-from-report action
28 | AttendanceNotPostedTodayListController | 5 | AttendanceNotPostedTodayListController.cs | — | — | Missing | Init, Index, AutoComplete, Download, Navigate — today's unposted list | Build today's unposted attendance dashboard widget/page
29 | GenerateAttendanceExcelController | 3 | GenerateAttendanceExcelController.cs | — | — | Missing | GenerateAttendanceExcel, Index [GET/POST] — dedicated Excel attendance generator | Build attendance Excel generator with configurable date ranges
30 | ImportAttendanceController | 13 | ImportAttendanceController.cs | import-attendance-upload, import-attendance-batches-list | /hr/import-attendance | Partial | VerifyToImportCSVAttendance, ImportCSVAttendance — CSV validation + import. ExcelDownload. Modern has file upload but verify CSV validation matches. | Verify CSV import validation matches legacy: column mapping, error handling, preview before import
31 | ImportBiometricAttendanceController | 14 | ImportBiometricAttendanceController.cs | — | — | Missing | ALL 14 methods missing: Create/Edit/Delete/Index CRUD for biometric records, ImportCSVAttendance, SaveImportAttendanceFile, VerifyToImportCSVAttendance, ExcelDownload | CRITICAL: Build biometric attendance import — device file parsing, CSV validation, punch timing extraction
32 | MobileAttendanceController | 7 | MobileAttendanceController.cs | mobile-attendance-list, mobile-attendance-approval-save | /hr/attendance-approval, /hr/my-attendance | Partial | MobileAttendanceApprovalODMap (Google Maps route), MobileAttendanceApprovalODList, MobileAttendanceDetailPopup — GPS route visualization missing | Build OD Map page with Google Maps showing employee GPS routes with markers
33 | MobileAttendanceApprovalController | 9 | MobileAttendanceApprovalController.cs | mobile-attendance-list (mode=approval) | /hr/attendance-approval | Partial | AttendanceDetail popup, _MobileAttendanceApproval partial, ShowAbsentList — detail popup and absent list | Verify attendance detail shows in modal; build absent list within approval page
34 | MobileAttendanceReportController | 2 | MobileAttendanceReportController.cs | — | — | Missing | Index, Report — mobile attendance report | Build mobile attendance report
35 | MyAttendanceController | 14 | MyAttendanceController.cs | mobile-attendance-list (mode=my) | /hr/my-attendance | Partial | ExcelDownload, Init/AutoComplete/Download/Navigate (server-side pagination + filtering). Legacy has 14 methods vs 1 modern page. | Add server-side filtering and Excel download to my-attendance page
36 | AbsentListController | 5 | AbsentListController.cs | — | — | Missing | Init, Index, AutoComplete, Download, Navigate — absent employees report | Build absent list report with filters and Excel download
37 | AbsentListTodayController | 9 | AbsentListTodayController.cs | — | — | Missing | Also includes AttendanceListForaPeriod methods. Init, Index, AutoComplete, Download, Navigate for both today's absent and period attendance. | Build today's absent list page
38 | EmpAttendanceListController | 2 | EmpAttendanceListController.cs | daily-attendance-list (filtered) | /hr/daily-attendance (filtered) | Migrated | Index [GET/POST] — covered by daily attendance with employee filter | Verify employee filter works
LEAVE & PERMISSION — 5 Legacy Controllers, 28 Methods
39 | LeaveFormController | 12 | LeaveFormController.cs | leave-forms-list, leave-form-save, leave-form-delete, leave-form-approval-save | /hr/leave-form | Migrated | ExcelDownload missing. Standard CRUD + approval present. | Add Excel download
40 | LeaveListTodayController | 5 | LeaveListTodayController.cs | — | — | Missing | Init, Index, AutoComplete, Download, Navigate — today's leave list report | Build today's leave report page
41 | CompOffAvailabilityController | 5 | CompOffAvailabilityController.cs | — | — | Missing | Init, Index, AutoComplete, Download, Navigate — comp-off availability tracking | Build comp-off availability report
42 | MobilePermissionController (in _shared.tsx) | 4 | via JsonMasterController | mobile-permissions-list, mobile-permission-save, mobile-permission-approval-save | /hr/permissions, /hr/permission-requests | Migrated | Permission close time tracking — verify actual end time update works | Verify permission close workflow
43 | DoNotDeductController | 12 | DoNotDeductController.cs | — | — | Missing | ALL 12 methods: CRUD for do-not-deduct exemptions (Index, Create, Edit, Delete, Details, ExcelDownload, AutoComplete, MenuTreeList) | Build do-not-deduct exemption CRUD (exempt employees from specific deductions)
SALARY & PAYROLL — 9 Legacy Controllers, 105 Methods
44 | SalaryCalculationController | ~20 | SalaryCalculationController.cs | monthly-salary-save/list, monthly-salary-details-list, payroll-actions, payroll-reports, salary-slip-pdf/data | /hr/salary-calculation, /hr/salary-calculation/new, /hr/salary-calculation/[id] | Migrated | Verify all payroll actions: import-attendance, mark-absent, recalculate, reprocess. 8 report types. ExcelDownload. | Verify payroll action chain and all 8 report formats match legacy
45 | SalaryFixationController | ~15 | SalaryFixationController.cs | salary-fixations-list, salary-fixation-details, salary-fixation-save | /hr/salary-fixation | Partial | Sub-detail views (SDFDList/SDFEList/SDVDList/SDVEList), ShowNetAmount, ExcelDownload — earning/deduction sub-lists | 1. Verify salary fixation Create/Edit (not just view) 2. Build sub-detail earning/deduction breakdown views
46 | EarningDeductionController | 13 | EarningDeductionController.cs | earning-deduction-save/list/delete, masters | /hr/earning-deductions | Migrated | UpdateEarningDeductionOrder (drag-drop reorder), GetEarningDeductionList (JSON), ExcelDownload | Add display order update endpoint and Excel download
47 | VariableEarningController | ~11 | VariableEarningController.cs | variable-earning-save/list/delete | /hr/variable-earning-deduction | Migrated | ExcelDownload, MenuTreeList missing | Add Excel download
48 | OTMonthlySalaryController | ~12 | via AttendanceController/OT endpoints | ot-monthly-salary-save/list/detail, ot-calculate | /hr/overtime related | Partial | Dedicated OT monthly salary page in legacy, modern combines with main overtime page. Verify OT salary calculation logic matches. | Verify OT salary calculation matches legacy formula
49 | LateFinePolicyController | 9 | LateFinePolicyController.cs | late-fine-policy-save/list/delete | (in settings) | Migrated | All CRUD present | Verify all fields match
50 | CreditTrackingController | 11 | CreditTrackingController.cs | credit-tracking-report | /hr/credit-tracking | Migrated | ExcelDownload, separate Create/Edit views. Modern uses report view. | Add CRUD operations if credit entries are manually created in legacy
51 | CreditTrackingListController | 12 | CreditTrackingListController.cs | credit-tracking-report | /hr/credit-tracking | Partial | GetCreditsTrackingSummary, GetCreditsTrackingSummaryPopup, GetLast6MonthsCreditsTrackingSummary, TransactionDetail, CreditTrackingListPDFDownload — summary, popup, 6-month trend, PDF export | 1. Add credit tracking summary widget 2. Add 6-month trend view 3. Add PDF download
ASSET MANAGEMENT — 10 Legacy Controllers, 114 Methods
52 | AssetController | 12 | AssetController.cs | — | — | Missing | ALL 12 methods: CRUD + ExcelDownload + MenuTreeList + AutoComplete for generic asset register | Check if covered by AssetMasterController/asset-master endpoints — may be duplicate
53 | AssetMasterController | 12 | AssetMasterController.cs | asset-master-save/list/delete, masters | /hr/assets | Migrated | ExcelDownload, GetAssetList (JSON). Standard CRUD present. | Add Excel download
54 | AssetStockController | 12 | AssetStockController.cs | asset-stock-save/list/delete | /hr/asset-stock | Migrated | ExcelDownload, MenuTreeList missing | Add Excel download
55 | AssetOpeningController | 12 | AssetOpeningController.cs | — | — | Missing | ALL 12 methods: CRUD for asset opening balance/stock (Create, Edit, Delete, ExcelDownload, GetItemList) | Build asset opening balance CRUD (initial stock entry)
56 | AssetPurchaseController | 20 | AssetPurchaseController.cs | — | — | Missing | ALL 20 methods: CRUD + AssetPurchaseDetail/SubDetail, GetAssetStockList, GetItem, ItemCategoryList, ItemList, ListItem, SaveAssetSubDetail — full purchase order management with line items | Build purchase order module with master-detail (purchase header + line items)
57 | AssetTransactionController | 12 | AssetTransactionController.cs | employee-asset-stock-save/list/delete | /hr/employee-asset-stock | Migrated | ExcelDownload, GetAssetList. Issue/return tracking present. | Add Excel download
58 | EmpAssetController | 12 | EmpAssetController.cs | employee-asset-save/list/delete | /hr/employee-asset | Migrated | ExcelDownload, MenuTreeList missing | Add Excel download
59 | EmpAssetStockController | 12 | EmpAssetStockController.cs | employee-asset-stock-save/list/delete | /hr/employee-asset-stock | Migrated | ExcelDownload, MenuTreeList missing | Add Excel download
60 | ItemCategoryController | 15 | ItemCategoryController.cs | — | — | Missing | ALL 15 methods: CRUD + ItemDetail, GetItem, ListItem, SaveItem — asset category/item master hierarchy | Build item category management with parent-child hierarchy
61 | AssetStockAnalysisController | 5 | AssetStockAnalysisController.cs | — | — | Missing | Init, Index, AutoComplete, Download, Navigate — stock analysis report | Build asset stock analysis report
62 | AssetTrackingAnalysisController | 5 | AssetTrackingAnalysisController.cs | — | — | Missing | Init, Index, AutoComplete, Download, Navigate — asset tracking report | Build asset tracking analysis report
RECRUITMENT — 8 Legacy Controllers, 73 Methods
63 | CandidateController | 6 | CandidateController.cs | candidates-list, candidate-save, candidate-delete | (shared page) | Partial | Application [GET/POST] (public application form), UpdatePickupStatus | Build public candidate application form and pickup status update
64 | InterviewController | 19 | InterviewController.cs | interviews-list, interview-save, interview-delete | (shared page) | Partial | GetCandidateDetails, GetJobPositionListByDepartmentId, ImportEmployee (convert candidate→employee), InterviewAttendanceEntry, InterviewIntimation [GET/POST], MarkTime, GetInterviewByMobileNo, ExcelDownload — 19 methods vs 3 modern endpoints | 1. Build import-to-employee conversion 2. Build interview attendance entry 3. Build interview intimation (notification) 4. Add time marking 5. Add job position lookup
65 | InterviewCandidateController | 11 | InterviewCandidateController.cs | candidates-list | (shared page) | Partial | Standard CRUD with ExcelDownload, AutoComplete. Modern has basic list/save. | Add Excel download and autocomplete
66 | InterviewCandidatedIntimationController | 12 | InterviewCandidatedIntimationController.cs | — | — | Missing | ALL 12 methods: CRUD for interview candidate notification/intimation with MenuTreeList | Build interview notification management (email/SMS to candidates)
67 | InterviewEducationController | 8 | InterviewEducationController.cs | — | — | Missing | DocList, Document, EducationList, GetData, Index, List, ShowEmployeeDocumentOnPopup, Edit | Build interview candidate education management with document upload
68 | InterviewFamilyController | 8 | InterviewFamilyController.cs | — | — | Missing | DocList, Document, GetData, Index, List, RelationList, ShowEmployeeDocumentOnPopup, Edit | Build interview candidate family details
69 | InterviewPreviousExperienceController | 4 | InterviewPreviousExperienceController.cs | — | — | Missing | GetData, Index, List, Edit — candidate previous experience | Build candidate previous experience management
70 | HonourListController | 5 | HonourListController.cs | — | — | Missing | Init, Index, AutoComplete, Download, Navigate — honour/blacklist management | Build honour/blacklist report
MASTER DATA — 6 Legacy Controllers, ~65 Methods
71 | DepartmentController | 11 | DepartmentController.cs | department-save/list/delete | /hr/departments | Migrated | ExcelDownload missing | Add Excel download
72 | DesignationController | 12 | DesignationController.cs | designation-save/list/delete | /hr/designations | Migrated | ExcelDownload, MenuTreeList missing | Add Excel download
73 | ShiftController | ~11 | ShiftController.cs | shift-save/list/delete | /hr/shifts | Migrated | ExcelDownload missing | Add Excel download
74 | CompanyHolidayController | 11 | CompanyHolidayController.cs | company-holiday-save/list/delete | /hr/company-holidays | Migrated | ExcelDownload missing | Add Excel download
75 | WeekOffController | ~11 | WeekOffController.cs | week-off-save/list/delete | /hr/week-offs | Migrated | ExcelDownload missing | Add Excel download
76 | JsonMasterController | 35 | JsonMasterController.cs | masters (aggregated), various endpoints | (used by all pages) | Partial | 35 JSON helper methods — most are dropdown data providers. Missing: GetAttendanceCompletedList, GetCompOffTrackingList, GetODDetailForApproval, GetPermissionDetailForApproval, fnCalculatePermissionUtilized, CalculateMaxWorkingHours, GetDiffTime, fnGetDiffInMins | Verify all dropdown data is available; build missing utility calculation endpoints
LOANS & ADVANCES — 2 Legacy Controllers, 23 Methods
77 | LoanAndAdvanceController | 11 | LoanAndAdvanceController.cs | loan-advance-save/list/delete | /hr/loan-advance | Migrated | ExcelDownload missing | Add Excel download
78 | LoanPrePaymentController | 12 | LoanPrePaymentController.cs | loan-prepayment-save/list/delete | /hr/loan-prepayment | Migrated | ExcelDownload, MenuTreeList missing | Add Excel download
REPORTS & ANALYTICS — 7 Legacy Controllers, ~32 Methods
79 | DashboardController | 2 | DashboardController.cs | dashboard | /hr/dashboard | Migrated | ShowDetail popup missing | Add dashboard detail popup
80 | AppointedReportController | 5 | AppointedReportController.cs | appointed-report-list | /hr/appointed-report | Migrated | Excel download (AppointedReportDownload) missing | Add Excel download
81 | HoldReportController | 5 | HoldReportController.cs | hold-report-list | /hr/hold-report | Migrated | Excel download missing | Add Excel download
82 | EntryExitAndLeaveSummaryController | 6 | EntryExitAndLeaveSummaryController.cs | entry-exit-leave-summary-list | /hr/entry-exit-leave-summary | Partial | DownloadSalaryVoucherTemplate, Excel download missing | Add salary voucher template download and Excel export
83 | AwardRatingController | 16 | AwardRatingController.cs | award-rating-save/list/delete | /hr/award-rating | Partial | ExcelDownload, ViewAwardRating (dedicated view page), ViewAwardRatingInit/AutoComplete/Download/Navigate — 16 legacy methods vs 3 modern | Build dedicated award rating view page with filters and Excel download
84 | MobileAttendanceReportController | 2 | MobileAttendanceReportController.cs | — | — | Missing | Index, Report — mobile attendance analysis report | Build mobile attendance report
ONBOARDING — New in Modern Stack (0 Legacy Controllers)
85 | — (New Feature) | 0 | N/A | onboarding-* endpoints (7 handlers) | /hr/onboarding, /hr/onboarding/new, /hr/onboarding/[id], /hr/onboarding/settings | New | New feature not in legacy: self-service onboarding with email/WhatsApp/SMS invite, status tracking, configurable fields | NEW FEATURE — no legacy equivalent. Already complete.
UTILITIES & BACKGROUND — 4 Legacy Controllers
86 | HomeController | 1 | HomeController.cs | dashboard | /hr/dashboard | Migrated | HR area landing page | Covered by dashboard
87 | UserMobileResetController | ~4 | via API | user-mobile-reset | /hr/user-mobile-reset | Migrated | All methods present | Verified
88 | ScheduledReportController | ~5 | ScheduledReportController.cs | scheduled-report-list | /hr/scheduled-report | Migrated | Excel download missing | Add Excel download
89 | PendingApprovalsController | ~5 | via JsonMasterController | pending-approvals-list | /hr/pending-approvals | Migrated | All present | Verified
BACKGROUND SCHEDULERS — Quartz.NET Jobs (NO Modern Equivalent)
90 | AttendancePostService (Quartz.NET) | N/A | AttendancePostService/Models/Scheduler.cs | — | — | Missing | PunchTimingsJob: Cron '0/30 * 7-23 * * ?' — processes mobile attendance into EmpDailyAttendance every 30 seconds from 7AM to 11PM | CRITICAL: Implement Go cron job for mobile→daily attendance posting
91 | AutoCloseAttendance (Background) | N/A | AttendanceController.cs | — | — | Missing | Closes all open attendance sessions at end of day to prevent data corruption | CRITICAL: Implement midnight auto-close job
92 | LocationUpdater (Background) | N/A | GeoLocationBO.cs | — | — | Missing | Batch geocoding: updates location names for GPS coordinates using Google Maps API | Build background job for batch geocoding

## Missing Features
# | Category | Feature | Legacy Controller(s) | Legacy Methods | Priority | Effort (Days) | Impact | Dependencies
1 | Background Jobs | AttendancePostService (mobile→daily posting) | AttendancePostService/Scheduler.cs | PunchTimingsJob (every 30s, 7AM-11PM) | Critical | 8 | Without this, mobile attendance won't flow into daily records. All attendance data incomplete. | Go cron library (robfig/cron)
2 | Background Jobs | AutoCloseAttendance | AttendanceController.cs | AutoCloseAttendance [GET/POST] | Critical | 3 | Open attendance sessions accumulate forever, corrupting reports and salary calculations | Scheduler from #1
3 | Background Jobs | LocationUpdater (batch geocoding) | GeoLocationBO.cs | GetGeoLocationNameV2, GetGeoLocationName | Medium | 5 | GPS coordinates won't have human-readable location names | Google Maps API key
4 | Attendance Reports | MonthlyAttendance view + report | AttendanceController.cs | MonthlyAttendance [GET/POST], MonthlyAttendanceReport, MonthlyAttendanceReportDownload | High | 5 | HR managers cannot review monthly attendance grid — key management tool | Daily attendance data
5 | Attendance Reports | AttendanceListForaPeriod | AttendanceListForaPeriodController.cs | 5 methods (Init, Index, AutoComplete, Download, Navigate) | High | 3 | Cannot query attendance for arbitrary date ranges | None
6 | Attendance Reports | AttendanceSummary report | AttendanceSummaryListController.cs | Index, DownloadTemplate | High | 3 | No summary/overview of attendance patterns | None
7 | Attendance Reports | DailyAttendanceReport (printable) | AttendanceController.cs | DailyAttendanceReport [GET/POST] | Medium | 3 | No printable daily register | None
8 | Attendance Reports | AttendanceNotPostedToday + Period | AttendanceNotPostedTodayListController.cs, AttendanceNotPostedPeriodListController.cs | 11 methods combined | High | 4 | Cannot monitor who hasn't submitted attendance — critical daily check | None
9 | Attendance Reports | AbsentList + AbsentListToday | AbsentListController.cs, AbsentListTodayController.cs | 14 methods combined | Medium | 4 | Cannot see absent employees at a glance | None
10 | Attendance | DailyAttendanceV2 (new version) | AttendanceController.cs | DailyAttendanceV2 [GET/POST], _DailyAttendanceV2, _DailyAttendanceV2Edit | Medium | 5 | Legacy already has V2 — modern should match latest version | None
11 | Attendance | Google Maps OD Route (MobileAttendanceApprovalODMap) | MobileAttendanceController.cs | MobileAttendanceApprovalODMap, MobileAttendanceApprovalODList | High | 5 | Managers can't verify field staff GPS routes on map | Google Maps API
12 | Biometric | Biometric attendance import | ImportBiometricAttendanceController.cs | 14 methods (full CRUD + CSV import + verify) | High | 10 | No automated attendance from biometric devices — manual entry only | Device documentation, hardware
13 | Employee | EmployeeTypeDetail (salary structure editor) | EmployeeTypeDetailController.cs | 11 methods (FD/FE/VD/VE indexes + lists + formula editor) | High | 8 | Cannot configure earning/deduction formulas per employee type | None
14 | Employee | EmployeeTypeAT (attendance type per emp type) | EmployeeTypeATController.cs | 4 methods | Medium | 2 | Cannot configure attendance rules per employee type | None
15 | Employee | EmployeeAttendanceDetail + List | EmployeeAttendanceDetailController.cs, EmployeeAttendanceListController.cs | 10 methods combined | Medium | 4 | No per-employee attendance detail view/report | None
16 | Employee | EmployeeSummary report | EmployeeSummaryListController.cs | 5 methods | Low | 3 | No employee summary report | None
17 | Employee | RecalculateSalary on type change | EmployeeTypeController.cs | RecalculateSalary, RecalculateSalaryProcess, LongRunningProcess | High | 5 | Changing employee type won't auto-recalculate salaries for affected employees | None
18 | Leave | LeaveListToday report | LeaveListTodayController.cs | 5 methods | Medium | 2 | Cannot see who's on leave today | None
19 | Leave | CompOff Availability | CompOffAvailabilityController.cs | 5 methods | Medium | 3 | Cannot track compensatory off balances | None
20 | Leave | DoNotDeduct exemptions | DoNotDeductController.cs | 12 methods (full CRUD) | Medium | 4 | Cannot exempt employees from specific deductions | None
21 | Salary | Credit Tracking advanced (summary, 6-month trend, PDF) | CreditTrackingListController.cs | 12 methods | Medium | 5 | Credit tracking limited to basic list — no analytics | None
22 | Salary | Salary fixation sub-detail views | SalaryFixationController.cs, EmployeeSalaryTrackingController.cs | SDFDList/SDFEList/SDVDList/SDVEList/SDLAList | Medium | 5 | Cannot see earning/deduction breakdown in salary fixation | None
23 | Asset | AssetPurchase (purchase orders) | AssetPurchaseController.cs | 20 methods (master-detail with line items) | Medium | 10 | No purchase order management for assets | None
24 | Asset | AssetOpening (opening balance) | AssetOpeningController.cs | 12 methods | Medium | 4 | Cannot set asset opening stock | None
25 | Asset | ItemCategory (asset hierarchy) | ItemCategoryController.cs | 15 methods | Medium | 5 | No asset category management with parent-child hierarchy | None
26 | Asset | AssetStockAnalysis + TrackingAnalysis | AssetStockAnalysisController.cs, AssetTrackingAnalysisController.cs | 10 methods combined | Low | 5 | No asset analysis reports | None
27 | Recruitment | InterviewCandidateIntimation (notifications) | InterviewCandidatedIntimationController.cs | 12 methods | Medium | 5 | Cannot send notifications to candidates | SMS/Email service
28 | Recruitment | Interview sub-forms (Education, Family, PrevExp) | InterviewEducationController.cs, InterviewFamilyController.cs, InterviewPreviousExperienceController.cs | 20 methods combined | Medium | 6 | Candidate profiles incomplete — no education/family/experience tracking | None
29 | Recruitment | ImportEmployee (candidate→employee conversion) | InterviewController.cs | ImportEmployee method | High | 3 | Cannot convert hired candidate to employee record | Employee save endpoint
30 | Recruitment | InterviewAttendanceEntry + MarkTime | InterviewController.cs | InterviewAttendanceEntry, MarkTime | Low | 2 | Cannot track interview attendance | None
31 | Recruitment | HonourList (honour/blacklist) | HonourListController.cs | 5 methods | Low | 2 | No candidate honour/blacklist report | None
32 | All Modules | Excel Download on every list page | All controllers | ExcelDownload method on ~40 controllers | Medium | 12 | Users lose export functionality they use daily | Excel library (excelize for Go)
33 | Reports | MobileAttendanceReport | MobileAttendanceReportController.cs | 2 methods | Medium | 3 | No mobile attendance analysis | None
34 | Reports | AwardRating dedicated view page | AwardRatingController.cs | ViewAwardRating, 4 helper methods | Low | 3 | No dedicated view for browsing awards/ratings | None
35 | Utility | JsonMaster utility calculations | JsonMasterController.cs | ~10 missing utility methods | Medium | 5 | Various dropdown data and calculation helpers missing | None
[5 empty] | TOTAL EFFORT | 0

## Migration Plan
Sprint | Week | Module | Task | Refs (Missing Feature #) | Effort (Days) | Owner | Status
SPRINT 1 — Critical Infrastructure (Weeks 1-2)
S1 | W1 | Scheduler | Set up Go cron job framework (robfig/cron or equivalent) | #1, #2 | 2 | Backend | Pending
S1 | W1 | Scheduler | Implement AttendancePostService — mobile→daily attendance posting (every 30s, 7AM-11PM) | #1 | 5 | Backend | Pending
S1 | W1-2 | Scheduler | Implement AutoCloseAttendance — midnight job to close open sessions | #2 | 3 | Backend | Pending
S1 | W2 | Attendance | Build MonthlyAttendance view + MonthlyAttendanceReport + download | #4 | 5 | Full Stack | Pending
SPRINT 2 — Attendance Reports (Weeks 3-4)
S2 | W3 | Attendance | Build AttendanceListForaPeriod report page | #5 | 3 | Full Stack | Pending
S2 | W3 | Attendance | Build AttendanceSummary report page | #6 | 3 | Full Stack | Pending
S2 | W3 | Attendance | Build AttendanceNotPostedToday + Period reports | #8 | 4 | Full Stack | Pending
S2 | W4 | Attendance | Build AbsentList + AbsentListToday pages | #9 | 4 | Full Stack | Pending
S2 | W4 | Attendance | Build Google Maps OD Route visualization | #11 | 5 | Frontend | Pending
SPRINT 3 — Employee & Salary Gaps (Weeks 5-6)
S3 | W5 | Employee | Build EmployeeTypeDetail (salary structure editor with FD/FE/VD/VE) | #13 | 8 | Full Stack | Pending
S3 | W5 | Employee | Implement RecalculateSalary on employee type change | #17 | 5 | Backend | Pending
S3 | W6 | Salary | Build salary fixation sub-detail views (earning/deduction breakdown) | #22 | 5 | Full Stack | Pending
S3 | W6 | Salary | Build credit tracking advanced (summary, 6-month trend, PDF export) | #21 | 5 | Full Stack | Pending
SPRINT 4 — Biometric & Missing Reports (Weeks 7-8)
S4 | W7 | Biometric | Build ImportBiometricAttendance (CSV import, validation, device parsing) | #12 | 10 | Full Stack | Pending
S4 | W7 | Attendance | Build DailyAttendanceReport (printable register) | #7 | 3 | Full Stack | Pending
S4 | W8 | Attendance | Build DailyAttendanceV2 (latest legacy version) | #10 | 5 | Full Stack | Pending
S4 | W8 | Reports | Build MobileAttendanceReport | #33 | 3 | Full Stack | Pending
SPRINT 5 — Leave, Deductions & Excel Export (Weeks 9-10)
S5 | W9 | Leave | Build LeaveListToday + CompOff Availability reports | #18, #19 | 5 | Full Stack | Pending
S5 | W9 | Leave | Build DoNotDeduct exemption CRUD | #20 | 4 | Full Stack | Pending
S5 | W9-10 | All | Add Excel download to all list pages (generic export component) | #32 | 12 | Full Stack | Pending
SPRINT 6 — Asset Management Gaps (Weeks 11-12)
S6 | W11 | Asset | Build AssetPurchase module (purchase orders with line items) | #23 | 10 | Full Stack | Pending
S6 | W11 | Asset | Build AssetOpening (opening balance) CRUD | #24 | 4 | Full Stack | Pending
S6 | W12 | Asset | Build ItemCategory (asset hierarchy) management | #25 | 5 | Full Stack | Pending
S6 | W12 | Asset | Build AssetStockAnalysis + TrackingAnalysis reports | #26 | 5 | Full Stack | Pending
SPRINT 7 — Recruitment Gaps (Weeks 13-14)
S7 | W13 | Recruitment | Build Interview sub-forms (Education, Family, PrevExp for candidates) | #28 | 6 | Full Stack | Pending
S7 | W13 | Recruitment | Build InterviewCandidateIntimation (email/SMS notifications) | #27 | 5 | Full Stack | Pending
S7 | W14 | Recruitment | Build ImportEmployee (candidate→employee conversion) | #29 | 3 | Backend | Pending
S7 | W14 | Recruitment | Build CandidateApplication (public form) + HonourList | #31 | 4 | Full Stack | Pending
SPRINT 8 — Utility & Polish (Weeks 15-16)
S8 | W15 | Scheduler | Build LocationUpdater background job (batch geocoding) | #3 | 5 | Backend | Pending
S8 | W15 | Employee | Build EmployeeTypeAT + EmployeeAttendanceDetail/List | #14, #15 | 6 | Full Stack | Pending
S8 | W16 | Utility | Build JsonMaster utility calculations + missing dropdowns | #35 | 5 | Backend | Pending
S8 | W16 | Reports | Build remaining reports (EmployeeSummary, AwardRating view, GenerateAttendanceExcel) | #16, #34, #30 | 8 | Full Stack | Pending
|  |  | TOTAL EFFORT |  | 0