## Executive Summary
HR Module Migration Gap Analysis
Legacy .NET (ASP.NET MVC + SQL Server) → Modern Stack (Go + Next.js + SQL Server)
Module | Legacy Controllers | Legacy Views | Modern Endpoints | Modern Pages | Status | Coverage %
Employee Master | 12 | 35 | 18 | 4 | Partial | 65%
Attendance & Time | 27 | 65 | 15 | 7 | Partial | 45%
Leave & Permission | 6 | 18 | 8 | 3 | Migrated | 85%
Payroll & Salary | 10 | 30 | 22 | 8 | Partial | 70%
Fines & Credits | 5 | 12 | 10 | 2 | Migrated | 80%
Asset Management | 13 | 28 | 12 | 4 | Partial | 55%
Recruitment & Interview | 10 | 25 | 6 | 2 | Partial | 35%
Shift & Schedule | 3 | 8 | 6 | 3 | Migrated | 90%
Master Data | 4 | 10 | 12 | 6 | Migrated | 95%
Loans & Advances | 2 | 6 | 6 | 2 | Migrated | 90%
Reports & Analytics | 8 | 20 | 8 | 7 | Partial | 50%
OT & Comp-off | 4 | 10 | 7 | 2 | Partial | 60%
Onboarding (NEW) | 0 | 0 | 4 | 3 | New Feature | 100%
Learning & Development | 2 | 5 | 0 | 0 | Missing | 0%
Biometric Integration | 3 | 8 | 0 | 0 | Missing | 0%
Background Schedulers | 4 | 0 | 0 | 0 | Missing | 0%
TOTAL | 113 | 280 | 134 | 53 | — | ~62%
Legend:
Migrated (≥80%)
Partial (20-79%)
Missing (0-19%)
TOP RISKS & BLOCKERS
1. Attendance module has 27 legacy controllers but only 15 modern endpoints — many report variants, auto-close, and biometric import missing
2. Background schedulers (Quartz.NET jobs: PunchTimingsJob, AttendancePostService, AutoCloseAttendance) have NO modern equivalent
3. Biometric device integration (Manju devices, punch timing imports) completely missing from Go stack
4. Employee sub-forms (Education, Family, Previous Experience, Nominee, Emergency Contact) exist as separate legacy controllers but are only tabs in one modern form — verify all CRUD operations work
5. Recruitment module only has candidate + interview list/save — missing interview scheduling, stages, requirement tracking, offer letter generation
6. Excel download functionality exists on EVERY legacy list page but is not implemented in modern stack
7. SMS notification system (employee updates, leave approvals, attendance alerts) not migrated
8. Learning & Development module completely missing (2 controllers, 5 views)
9. Workflow/approval chain system — legacy has multi-level approval for Leave, Employee changes — modern has basic single-level only
10. Auto-user creation linked to employee creation in legacy — verify this exists in modern onboarding flow

## Detailed Gap Analysis
Module | Legacy Page / Action | HTTP Verb | Modern Endpoint | Modern Next.js Page | Status | Missing Fields/Logic | Priority | Notes
EMPLOYEE MASTER (12 legacy controllers → 4 modern pages)
Employee Master | Index (Employee List) | GET | employees-list | /hr/employees | Migrated | Excel download missing | Medium | Core list works
Employee Master | Create (New Employee Form) | GET/POST | employee-save | /hr/employees/new | Migrated | Auto-user creation needs verification | High | 7-tab form in modern
Employee Master | Edit (Employee Edit Form) | GET/POST | employee-save | /hr/employees/[id]/edit | Migrated | All tabs need field-by-field check | High
Employee Master | Details (Read-only view) | GET | employee-get | /hr/employees/[id] | Partial | Separate detail page may not exist | Low | Edit page may serve as detail
Employee Master | Delete | POST | employee-delete | (inline action) | Migrated |  | Low
Employee Master | ExcelDownload | GET | — | — | Missing | Full Excel export of employee list | Medium | Common in all legacy lists
Employee Master | AutoComplete (search) | GET | employees-list (search param) | (inline) | Migrated |  | Low
Employee Master | EmployeeEducation (CRUD) | GET/POST | employee-save (tab) | /hr/employees/[id]/edit (tab) | Partial | Separate controller in legacy → tab in modern; verify Create/Edit/Delete all work | High | Was separate controller
Employee Master | EmployeeFamily (CRUD) | GET/POST | employee-save (tab) | /hr/employees/[id]/edit (tab) | Partial | Same as above — verify sub-form CRUD | High | Was separate controller
Employee Master | PreviousExperience (CRUD) | GET/POST | employee-save (tab) | /hr/employees/[id]/edit (tab) | Partial | Same as above | Medium | Was separate controller
Employee Master | EmployeeNominee (CRUD) | GET/POST | employee-save (tab) | /hr/employees/[id]/edit (tab) | Partial | Same as above | Medium | Was separate controller
Employee Master | EmergencyContact (CRUD) | GET/POST | employee-save (tab) | /hr/employees/[id]/edit (tab) | Partial | Same as above | Medium | Was separate controller
Employee Master | EmployeeDocument (upload/list) | GET/POST | employee-document-save/list | /hr/employees/[id]/edit (tab) | Partial | Verify file upload/download works | High
Employee Master | ChangePassword | POST | — | — | Missing | Employee password change from HR module | Low | May be in auth module
Employee Master | ProfilePhoto upload | POST | employee-save | /hr/employees/[id]/edit | Partial | Verify image upload field exists | Medium
Employee Master | SMS on employee create/update | — | — | — | Missing | SMS notification on employee events | Low | Entire SMS subsystem missing
ATTENDANCE & TIME (27 legacy controllers → 7 modern pages)
Attendance | DailyAttendanceList (Index) | GET/POST | daily-attendance-list | /hr/daily-attendance | Migrated | Dept filter, employee filter work | — | Core page works
Attendance | DailyAttendance Create/Edit | GET/POST | daily-attendance-save | /hr/daily-attendance (modal) | Migrated |  | —
Attendance | DailyAttendance Delete | POST | daily-attendance-delete | (inline) | Migrated |  | —
Attendance | MobileAttendanceApproval (Index) | GET/POST | mobile-attendance-list (mode=approval) | /hr/attendance-approval | Migrated | Map review (Google Maps route) missing | High | Legacy has ODMap with Google markers
Attendance | SaveMobileAttendanceApproval | POST | mobile-attendance-approval-save | /hr/attendance-approval (modal) | Migrated |  | —
Attendance | MyAttendance (Index) | GET | mobile-attendance-list (mode=my) | /hr/my-attendance | Migrated |  | —
Attendance | ImportAttendance (Excel upload) | GET/POST | import-attendance-upload | /hr/import-attendance | Migrated | Verify Excel parsing matches legacy format | High
Attendance | ImportAttendanceBatches List | GET | import-attendance-batches-list | /hr/import-attendance | Migrated |  | —
Attendance | AttendanceListForaPeriod | GET/POST | — | — | Missing | Period-based attendance report with filters | High | Major report page
Attendance | AttendanceNotPostedToday | GET | — | — | Missing | Dashboard widget: who hasn't posted today | High | Used for daily monitoring
Attendance | AttendanceNotPostedPeriod | GET/POST | — | — | Missing | Period-based not-posted report | Medium | Variant of above
Attendance | AttendanceSummary | GET/POST | — | — | Missing | Monthly summary per employee | High | Key HR report
Attendance | AbsentList / AbsentListToday | GET/POST | — | — | Missing | Absent employee list (daily + period) | Medium
Attendance | DailyAttendanceReport | GET/POST | — | — | Missing | Printable daily attendance register | Medium
Attendance | AutoCloseAttendance | POST | — | — | Missing | Auto-close open attendance at day end | High | Critical background logic
Attendance | MobileAttendanceApprovalODMap | GET | — | — | Missing | Google Maps route visualization with markers | Medium | Shows employee GPS route on map
Attendance | GetMobileAttendanceApprovalCount | GET | pending-approvals-list | /hr/pending-approvals | Partial | Count-only endpoint vs full list | Low
Attendance | AttendanceRectificationFromExcel | POST | — | — | Missing | Bulk attendance correction from Excel | Medium | Admin utility
Attendance | BiometricAttendance Import | POST | — | — | Missing | Manju device biometric data import | High | Hardware integration
Attendance | PunchTimings Import/Process | POST | — | — | Missing | Biometric punch timing processing | High | Related to biometric
Attendance | Excel Download (all lists) | GET | — | — | Missing | Excel export on every attendance list | Medium | Common pattern
Attendance | MobileAttendanceProcessing | — | — | — | Missing | Background: UpdateDistanceAndLocation | Medium | Quartz.NET job
Attendance | AttendancePostService | — | — | — | Missing | Quartz.NET: auto-post attendance every 30s | Critical | Core background service
Attendance | PunchTimingsJob | — | — | — | Missing | Quartz.NET: process punch timings 7AM-11PM | Critical | Core background service
LEAVE & PERMISSION (6 legacy controllers → 3 modern pages)
Leave | LeaveForm Index (List) | GET/POST | leave-forms-list | /hr/leave-form | Migrated |  | —
Leave | LeaveForm Create/Edit | GET/POST | leave-form-save | /hr/leave-form (modal) | Migrated |  | —
Leave | LeaveForm Approval | POST | leave-form-approval-save | /hr/leave-form (action) | Migrated | Multi-level approval chain missing | High | Legacy has workflow system
Leave | LeaveForm Delete | POST | leave-form-delete (implied) | /hr/leave-form (action) | Partial | Verify delete endpoint exists | Low
Leave | CompOff Request (CRUD) | GET/POST | — | — | Missing | Compensatory off request form | Medium | Was separate controller
Leave | MobilePermission Index | GET/POST | mobile-permissions-list | /hr/permission-requests | Migrated |  | —
Leave | MobilePermission Create/Edit | GET/POST | mobile-permission-save | /hr/permission-requests (modal) | Migrated |  | —
Leave | MobilePermission Approval | POST | mobile-permission-approval-save | /hr/permission-requests (action) | Migrated |  | —
Leave | Permission Close (end time) | POST | mobile-permission-save (update) | — | Partial | Close permission with actual end time | Medium | May need dedicated endpoint
Leave | SMS on Leave Approval | — | — | — | Missing | SMS notification on approve/reject | Low
Leave | Leave Balance Report | GET | — | — | Missing | Remaining leave balance per employee | High | Key HR report
Leave | Excel Download (leave list) | GET | — | — | Missing | Excel export | Medium
PAYROLL & SALARY (10 legacy controllers → 8 modern pages)
Payroll | SalaryCalculation Index | GET/POST | monthly-salary-list | /hr/salary-calculation | Migrated |  | —
Payroll | SalaryCalculation Create | GET/POST | monthly-salary-save | /hr/salary-calculation/new | Migrated | Verify all employee type filters | Medium
Payroll | SalaryCalculation Detail | GET | monthly-salary-details-list | /hr/salary-calculation/[id] | Migrated |  | —
Payroll | SalarySlip View/PDF | GET | salary-slip-data / salary-slip-pdf | (inline view) | Migrated | Verify PDF generation matches legacy format | High
Payroll | Salary Fixation List | GET/POST | salary-fixations-list | /hr/salary-fixation | Migrated |  | —
Payroll | Salary Fixation Detail | GET | salary-fixation-details | /hr/salary-fixation (modal) | Migrated | Earning/deduction breakdown | —
Payroll | Salary Fixation Create/Edit | GET/POST | salary-fixation-save (implied) | — | Partial | Verify create/edit endpoints exist | High | May only have list+detail
Payroll | Salary Tracking List | GET/POST | salary-tracking-list | /hr/salary-tracking | Migrated |  | —
Payroll | PF/ESI Analysis | GET | monthly-salary-pf-esi-analysis | /hr/pf-esi-analysis/[id] | Migrated |  | —
Payroll | PF/ESI List | GET | monthly-salary-pf-esi-list | /hr/pf-esi-analysis/[id] | Migrated |  | —
Payroll | Payroll Actions (import/recalc) | POST | payroll-actions | (inline action) | Migrated | 4 actions: import-attendance, mark-absent, recalculate, reprocess | —
Payroll | Payroll Reports | POST | payroll-reports | (download) | Migrated | 8 report types: salary-list, salary-detail, salary-bank, salary-slip, pf-statement, pf-summary, esi-statement, esi-summary | —
Payroll | Variable Earning/Deduction CRUD | GET/POST | variable-earning-save/list/delete | /hr/variable-earning-deduction | Migrated |  | —
Payroll | Earning Deduction Master CRUD | GET/POST | earning-deduction-save/list/delete | /hr/earning-deductions | Migrated |  | —
Payroll | Bank Transfer Report | GET | payroll-reports (type=salary-bank) | (download) | Migrated |  | —
Payroll | SalaryCalculation ExcelDownload | GET | — | — | Missing | Separate Excel export of salary sheet | Medium
Payroll | Salary Revision History | GET | — | — | Missing | Historical salary changes per employee | Low
FINES & CREDITS (5 legacy controllers → 2 modern pages)
Fines | EmployeeFine Index (List) | GET/POST | employee-fines-list + employee-fines-v2-list | /hr/employee-fines | Migrated | V1 and V2 both exist in modern | —
Fines | EmployeeFine Create/Edit | GET/POST | employee-fine-save + employee-fine-v2-save | /hr/employee-fines (modal) | Migrated |  | —
Fines | EmployeeFine Waive | POST | employee-fine-waive | /hr/employee-fines (action) | Migrated |  | —
Fines | EmployeeFine Delete | POST | employee-fine-delete + employee-fine-v2-delete | /hr/employee-fines (action) | Migrated |  | —
Fines | LateFinePolicy CRUD | GET/POST | late-fine-policy-save/list/delete | (settings page) | Migrated |  | —
Fines | CreditTracking Report | GET | credit-tracking-report | /hr/credit-tracking | Migrated | Balance ledger + type-wise summary | —
Fines | FineSlab Master CRUD | GET/POST | — | — | Missing | Fine slab configuration master | Medium | Legacy had FineSlabController
Fines | FineExemption CRUD | GET/POST | — | — | Missing | Fine exemption management | Low
ASSET MANAGEMENT (13 legacy controllers → 4 modern pages)
Assets | AssetMaster CRUD | GET/POST | asset-master-save/list/delete | /hr/assets | Migrated |  | —
Assets | AssetStock CRUD | GET/POST | asset-stock-save/list/delete | /hr/asset-stock | Migrated |  | —
Assets | EmployeeAsset CRUD | GET/POST | employee-asset-save/list/delete | /hr/employee-asset | Migrated |  | —
Assets | EmployeeAssetStock CRUD | GET/POST | employee-asset-stock-save/list/delete | /hr/employee-asset-stock | Migrated | Issue/return tracking | —
Assets | AssetPurchase CRUD | GET/POST | — | — | Missing | Purchase order management for assets | Medium | Separate controller in legacy
Assets | AssetMaintenance CRUD | GET/POST | — | — | Missing | Maintenance schedule & history | Medium
Assets | AssetTransfer CRUD | GET/POST | — | — | Missing | Transfer between employees | Medium
Assets | AssetDisposal CRUD | GET/POST | — | — | Missing | Write-off / disposal tracking | Low
Assets | AssetReport (various) | GET | — | — | Missing | Asset value report, depreciation, allocation report | Medium | Multiple report variants
Assets | AssetBarcode/QR | GET | — | — | Missing | Barcode/QR generation for tracking | Low
Assets | AssetCategory CRUD | GET/POST | — | — | Missing | Asset category master | Medium
Assets | Excel Download (all asset lists) | GET | — | — | Missing | Excel export for every list | Medium
RECRUITMENT & INTERVIEW (10 legacy controllers → 2 modern pages)
Recruitment | Candidate List | GET/POST | candidates-list | (shared page) | Migrated |  | —
Recruitment | Candidate Create/Edit | GET/POST | candidate-save | (shared page) | Migrated |  | —
Recruitment | Candidate Delete | POST | candidate-delete | (inline) | Migrated |  | —
Recruitment | Interview List | GET/POST | interviews-list | (shared page) | Migrated |  | —
Recruitment | Interview Schedule/Create | GET/POST | interview-save | (shared page) | Partial | Verify scheduling fields exist | High
Recruitment | Interview Stages (multi-round) | GET/POST | — | — | Missing | First/second interviewer, stage tracking | High | Legacy has FirstInterviewStage, SecondInterviewStage
Recruitment | RequirementPosting CRUD | GET/POST | — | — | Missing | Job requirement/vacancy posting | High | Was separate controller
Recruitment | OfferLetter Generation | GET/POST | — | — | Missing | Offer letter template + generation | Medium
Recruitment | InterviewSource Master | GET/POST | — | — | Missing | Source of candidates (LinkedIn, referral, etc.) | Medium | Master data
Recruitment | CandidateDocument Upload | GET/POST | — | — | Missing | Resume/document uploads for candidates | Medium
Recruitment | Recruitment Report | GET | — | — | Missing | Hiring pipeline, source effectiveness | Low
Recruitment | Interview Calendar View | GET | — | — | Missing | Calendar view of scheduled interviews | Low
Recruitment | Excel Download | GET | — | — | Missing | Export lists | Medium
SHIFT, SCHEDULE & MASTER DATA (7 legacy controllers → 9 modern pages)
Master | Shift CRUD | GET/POST | shift-save/list/delete | /hr/shifts | Migrated | All fields present | —
Master | Department CRUD | GET/POST | department-save/list/delete | /hr/departments | Migrated |  | —
Master | Designation CRUD | GET/POST | designation-save/list/delete | /hr/designations | Migrated | Job description, package range, skills | —
Master | WeekOff CRUD | GET/POST | week-off-save/list/delete | /hr/week-offs | Migrated | Dept/employee selection | —
Master | CompanyHoliday CRUD | GET/POST | company-holiday-save/list/delete | /hr/company-holidays | Migrated |  | —
Master | AttendanceType CRUD | GET/POST | attendance-type-save/list/delete | /hr/attendance-types | Migrated |  | —
Master | EmployeeType CRUD | GET/POST | employee-type-save/list/delete | /hr/employee-types | Migrated |  | —
Master | Qualification CRUD | GET/POST | qualification-save/list/delete | /hr/qualifications | Migrated |  | —
Master | ShiftAssignment (bulk assign) | GET/POST | — | — | Missing | Assign shifts to multiple employees at once | Medium | Was separate in legacy
LOANS & ADVANCES (2 legacy controllers → 2 modern pages)
Loans | LoanAdvance List | GET/POST | loan-advances-list | /hr/loan-advance | Migrated |  | —
Loans | LoanAdvance Create/Edit | GET/POST | loan-advance-save | /hr/loan-advance (modal) | Migrated | All fields: loan no, installments, deduction from | —
Loans | LoanAdvance Delete | POST | loan-advance-delete | (inline) | Migrated |  | —
Loans | LoanPrepayment List | GET/POST | loan-prepayments-list | /hr/loan-prepayment | Migrated |  | —
Loans | LoanPrepayment Create/Edit | GET/POST | loan-prepayment-save | /hr/loan-prepayment (modal) | Migrated |  | —
Loans | LoanPrepayment Delete | POST | loan-prepayment-delete | (inline) | Migrated |  | —
OVERTIME & COMP-OFF (4 legacy controllers → 2 modern pages)
OT | Overtime List | GET/POST | overtime-list | /hr/overtime | Migrated |  | —
OT | Overtime Create/Edit | GET/POST | overtime-save | /hr/overtime (modal) | Migrated |  | —
OT | Overtime Delete | POST | overtime-delete | (inline) | Migrated |  | —
OT | OT Salary Calculation | POST | ot-monthly-salary-save + ot-calculate | (implied page) | Migrated | Verify OT amount per hour logic | High
OT | OT Salary Detail View | GET | ot-monthly-salary-detail-list | (detail page) | Migrated |  | —
OT | CompOff CRUD | GET/POST | — | — | Missing | Compensatory off entry and approval | Medium | Was separate controller
OT | OT Report | GET | — | — | Missing | OT summary/analysis report | Low
REPORTS & ANALYTICS (8 legacy controllers → 7 modern pages)
Reports | Dashboard | GET | dashboard | /hr/dashboard | Migrated | 6 KPI cards | —
Reports | Pending Approvals | GET | pending-approvals-list | /hr/pending-approvals | Migrated | Attendance, followup, workflow counts | —
Reports | Appointed Report | GET | appointed-report-list | /hr/appointed-report | Migrated |  | — | New in modern
Reports | Hold Report | GET | hold-report-list | /hr/hold-report | Migrated |  | — | New in modern
Reports | Entry/Exit/Leave Summary | GET | entry-exit-leave-summary-list | /hr/entry-exit-leave-summary | Migrated |  | — | New in modern
Reports | Scheduled Report | GET | scheduled-report-list | /hr/scheduled-report | Migrated |  | — | New in modern
Reports | DailyAttendanceReport | GET/POST | — | — | Missing | Printable daily attendance register | High | Key legacy report
Reports | MonthlyAttendanceReport | GET/POST | — | — | Missing | Monthly attendance summary grid | High | Key legacy report
Reports | SalaryStatement Report | GET/POST | payroll-reports | (covered in payroll) | Migrated | 8 report types | —
Reports | HeadcountReport | GET/POST | — | — | Missing | Active/inactive headcount by dept | Medium
Reports | AttritionReport | GET/POST | — | — | Missing | Employee exit analysis | Low
Reports | BiometricReport | GET/POST | — | — | Missing | Biometric punch timing analysis | Medium | Depends on biometric integration
ONBOARDING (New in Modern — 0 legacy, 3 modern pages)
Onboarding | Onboarding Page | — | onboarding endpoints | /hr/onboarding | New Feature | Status tabs, batch sending, templates | — | Not in legacy
Onboarding | Onboarding Settings | — | onboarding-settings endpoints | /hr/onboarding/settings | New Feature | Email templates, workflow config | — | Not in legacy
Onboarding | Public Onboarding Form | — | onboarding-public endpoints | /hr/onboarding/public | New Feature | Self-service employee onboarding | — | Not in legacy
COMPLETELY MISSING MODULES
Learning | CourseManagement CRUD | GET/POST | — | — | Missing | Training course creation and management | Medium | 2 controllers in legacy
Learning | TrainingAttendance | GET/POST | — | — | Missing | Track employee training participation | Medium
Learning | LearningReport | GET | — | — | Missing | Training completion reports | Low
Biometric | BiometricDevice Management | GET/POST | — | — | Missing | Manju device config, connection, sync | High | 3 controllers in legacy
Biometric | PunchTiming Import | POST | — | — | Missing | Import from biometric devices | High | Critical for attendance
Biometric | PunchTiming Report | GET | — | — | Missing | Raw punch timing analysis | Medium
Scheduler | AttendancePostService | — | — | — | Missing | Quartz.NET: auto-post every 30s (7AM-11PM) | Critical | Core business process
Scheduler | PunchTimingsJob | — | — | — | Missing | Quartz.NET: mobile punch processing | Critical | Core business process
Scheduler | AutoCloseAttendance | — | — | — | Missing | Auto-close open sessions at midnight | Critical | Prevents data corruption
Scheduler | LocationUpdater | — | — | — | Missing | Batch update GPS location names | Medium | Background utility
Utility | UserMobileReset | POST | user-mobile-reset | /hr/user-mobile-reset | Migrated |  | —

## Field-Level Comparison
Page | Field Name | Legacy Column/Field | Modern Column/Field | Data Type | Status | Notes
Employee Form | Employee Code | EmployeeCode | employeeCode | string | Migrated
Employee Form | Employee Name | EmployeeName | employeeName | string | Migrated
Employee Form | Date of Birth | DateOfBirth | dateOfBirth | date | Migrated
Employee Form | Date of Joining | DateOfJoining | dateOfJoining | date | Migrated
Employee Form | Department | DepartmentId | departmentId | int/FK | Migrated | Dropdown
Employee Form | Designation | DesignationId | designationId | int/FK | Migrated | Cascading from dept
Employee Form | Shift | ShiftId | shiftId | int/FK | Migrated | Dropdown
Employee Form | Employee Type | EmployeeTypeId | employeeTypeId | int/FK | Migrated
Employee Form | Gender | Gender | gender | string | Migrated
Employee Form | Blood Group | BloodGroup | bloodGroup | string | Migrated
Employee Form | Mobile Number | MobileNumber | mobileNumber | string | Migrated
Employee Form | Email | Email | email | string | Migrated
Employee Form | Address | Address | address | string | Migrated
Employee Form | City | City | city | string | Migrated
Employee Form | State | State | state | string | Migrated
Employee Form | Pincode | Pincode | pincode | string | Migrated
Employee Form | Aadhar Number | AadharNumber | aadharNumber | string | Migrated
Employee Form | PAN Number | PANNumber | panNumber | string | Migrated
Employee Form | EPF Number | EPFNumber | epfNumber | string | Migrated
Employee Form | ESI Number | ESINumber | esiNumber | string | Migrated
Employee Form | Bank Account No | BankAccountNumber | accountNumber | string | Migrated | Field name differs
Employee Form | Bank Name | BankName | bankName | string | Migrated
Employee Form | IFSC Code | IFSCCode | ifscCode | string | Migrated
Employee Form | Father Name | FatherName | fatherName | string | Migrated
Employee Form | Qualification | QualificationId | qualificationId | int/FK | Migrated
Employee Form | Experience | Experience | experience | string | Migrated
Employee Form | Previous Company | PreviousCompany | — | string | Missing | Check if in modern form
Employee Form | Reference Name | ReferenceName | — | string | Partial | Verify field exists
Employee Form | Profile Photo | ProfilePhotoPath | profilePhotoUrl | file | Partial | Verify upload works
Employee Form | Probation End Date | ProbationEndDate | probationEndDate | date | Migrated | Auto-calculated
Employee Form | IsActive | IsActive | isActive | bool | Migrated
Employee Form | Reporting Manager | ReportingToUserId | reportingToUserId | int/FK | Migrated
Employee Form | Auto-create User | CreateUserFlag | — | bool | Missing | Legacy auto-creates login user
Employee Form | SMS on Create | SendSMS | — | bool | Missing | SMS subsystem not migrated
Daily Attendance | Employee | EmployeeId | employeeId | int/FK | Migrated
Daily Attendance | Date | DateAndTime | dateAndTime | date | Migrated
Daily Attendance | Morning Session | MorningSession | morningSession | string | Migrated | P/A/H/WO/etc
Daily Attendance | Evening Session | EveningSession | eveningSession | string | Migrated
Daily Attendance | In Time | InTime | inTime | time | Migrated
Daily Attendance | Out Time | OutTime | outTime | time | Migrated
Daily Attendance | Total Hours | TotalHours | totalHours | decimal | Migrated
Daily Attendance | OT Minutes | OTInMins | otInMins | int | Migrated
Daily Attendance | Working Duration | WorkingDurationInMins | workingDurationInMins | int | Migrated
Daily Attendance | Attendance Value | AttendanceValue | attendanceValue | decimal | Migrated | 0, 0.5, 1
Daily Attendance | Morning Remarks | MorningRemarks | morningRemarks | string | Migrated
Daily Attendance | Evening Remarks | EveningRemarks | eveningRemarks | string | Migrated
Daily Attendance | Is Verified | IsVerified | isVerified | bool | Migrated
Daily Attendance | Shift | ShiftDescription | shiftDescription | string | Migrated | Display only
Mobile Attendance | Employee | EmployeeId | employeeId | int/FK | Migrated
Mobile Attendance | In Date/Time | InDateAndTime | inDateAndTime | datetime | Migrated
Mobile Attendance | Out Date/Time | OutDateAndTime | outDateAndTime | datetime | Migrated
Mobile Attendance | Total Duration (mins) | TotalDurationInMins | totalDurationInMins | int | Migrated
Mobile Attendance | Late Entry (mins) | LateEntryDurationInMins | lateEntryDurationInMins | int | Migrated
Mobile Attendance | Early Exit (mins) | EarlyExitDurationInMins | earlyExitDurationInMins | int | Migrated
Mobile Attendance | Starting Location | StartingLocation | startingLocation | string | Migrated | Geocoded
Mobile Attendance | Ending Location | EndingLocation | endingLocation | string | Migrated
Mobile Attendance | Starting Lat/Lng | StartingLatitude/Longitude | startingLatitude/Longitude | decimal | Migrated
Mobile Attendance | Ending Lat/Lng | EndingLatitude/Longitude | endingLatitude/Longitude | decimal | Migrated
Mobile Attendance | Need Approval | NeedApproval | needApproval | bool | Migrated
Mobile Attendance | Approved Attendance | ApprovedAttendance | approvedAttendance | string | Migrated
Mobile Attendance | Approval Remarks | ApprovalRemarks | approvalRemarks | string | Migrated
Mobile Attendance | Punch Timings | PunchTimings | punchTimings | string | Migrated | Concatenated
Mobile Attendance | OD Map View | MobileAttendanceApprovalODMap | — | view | Missing | Google Maps route visualization
Mobile Attendance | Battery % | BatteryPercentage | — | int | Missing | Device metadata not in approval view
Mobile Attendance | GPS On/Off | IsGPSOn | — | bool | Missing | Device metadata
Mobile Attendance | WiFi On/Off | IsWifiOn | — | bool | Missing | Device metadata
Mobile Attendance | Signal Strength | SignalStrength | — | int | Missing | Device metadata
Mobile Attendance | App Version | AppVersion | — | string | Missing | Device metadata
Salary Calculation | Employee Code | EmployeeCode | employeeCode | string | Migrated
Salary Calculation | Employee Name | EmployeeName | employeeName | string | Migrated
Salary Calculation | Department | DepartmentName | departmentName | string | Migrated
Salary Calculation | Total Working Hours | TotalWorkingHours | totalWorkingHours | decimal | Migrated
Salary Calculation | Total Working Days | TotalWorkingDays | totalWorkingDays | decimal | Migrated
Salary Calculation | Salary Working Hours | SalaryWorkingHours | salaryWorkingHours | decimal | Migrated
Salary Calculation | Salary Working Days | SalaryWorkingDays | salaryWorkingDays | decimal | Migrated
Salary Calculation | Extra Hours | ExtraHours | extraHours | decimal | Migrated
Salary Calculation | Shortage Hours | ShortageHours | shortageHours | decimal | Migrated
Salary Calculation | Per Minute Salary | PerMinSalary | perMinSalary | decimal | Migrated
Salary Calculation | Basic Salary | BasicSalary | basicSalary | decimal | Migrated
Salary Calculation | Fixed Earnings | FixedEarnings | fixedEarnings | decimal | Migrated
Salary Calculation | Variable Earnings | VariableEarnings | variableEarnings | decimal | Migrated
Salary Calculation | Fixed Deductions | FixedDeductions | fixedDeductions | decimal | Migrated
Salary Calculation | Variable Deductions | VariableDeductions | variableDeductions | decimal | Migrated
Salary Calculation | Total Payment | TotalPayment | totalPayment | decimal | Migrated
Salary Calculation | Salary Slip PDF | SalarySlipFilePath | salarySlipFilePath | string | Migrated | PDF generation

## Action Items
# | Priority | Module | Action Item | Effort (Days) | Dependencies | Risk if Not Done
1 | Critical | Scheduler | Implement background job framework (Go equivalent of Quartz.NET) for AttendancePostService, PunchTimingsJob, AutoCloseAttendance | 15 | Go cron library selection | Attendance data will be incomplete/corrupt without auto-posting
2 | Critical | Attendance | Build AttendanceListForaPeriod + AttendanceSummary reports | 8 | Daily attendance data | HR managers cannot review attendance patterns
3 | Critical | Attendance | Implement AutoCloseAttendance logic (close open sessions at midnight) | 3 | Scheduler framework | Open sessions accumulate, attendance data corrupted
4 | High | Attendance | Build MobileAttendanceApprovalODMap (Google Maps route visualization) | 5 | Google Maps API key | Managers can't verify field staff routes
5 | High | Attendance | Build AttendanceNotPostedToday dashboard widget | 3 | None | Daily monitoring not possible
6 | High | Biometric | Implement biometric device integration (Manju device punch import) | 10 | Device documentation, hardware access | Manual attendance only — defeats automation
7 | High | Employee | Verify all sub-form CRUD (Education, Family, Experience, Nominee, Emergency Contact) actually works end-to-end | 5 | None | Employee data incomplete
8 | High | Employee | Implement auto-user creation on employee save | 3 | Auth/user module | Manual user creation needed for each employee
9 | High | Payroll | Verify salary fixation Create/Edit endpoints exist (not just List+Detail) | 2 | None | Can't set up new employee salaries
10 | High | Recruitment | Build interview stages (multi-round) and requirement posting | 8 | None | Recruitment process incomplete
11 | High | Leave | Build Leave Balance Report | 3 | Leave form data | HR can't check remaining leaves
12 | High | Leave | Implement multi-level approval workflow (matching legacy chain) | 8 | Workflow engine | Single-level approval insufficient for org hierarchy
13 | Medium | All Modules | Add Excel download to every list page | 10 | Excel generation library | Users lose daily-use export functionality
14 | Medium | Attendance | Build AbsentList + AbsentListToday | 3 | None
15 | Medium | Attendance | Build DailyAttendanceReport (printable register) | 3 | None
16 | Medium | Assets | Build AssetPurchase, AssetMaintenance, AssetTransfer controllers | 10 | None | Asset lifecycle management incomplete
17 | Medium | Leave | Build CompOff (Compensatory Off) CRUD | 3 | None
18 | Medium | Reports | Build HeadcountReport, MonthlyAttendanceReport | 5 | None
19 | Medium | Fines | Build FineSlab master CRUD | 2 | None
20 | Medium | OT | Build CompOff CRUD + OT Report | 3 | None
21 | Low | Learning | Build Learning & Development module (Course management, training attendance) | 15 | None | Training tracking not available
22 | Low | All Modules | Implement SMS notification subsystem | 8 | SMS provider API | No automated notifications
23 | Low | Recruitment | Build OfferLetter, CandidateDocument, Calendar view | 8 | None
24 | Low | Reports | Build AttritionReport, BiometricReport | 5 | None
|  |  | TOTAL ESTIMATED EFFORT | 148